## SAFAPAC
Task | Status | Start date | End date | Where? | Notes
added x and y axis visibility | Completed | 2025-12-01 | 2025-12-01 | Breakevenbarchart.js
subscript CO2 | Completed | 2025-12-01 | 2025-12-01 | biofuelform.js analysisdashboard.js
remove double negative | Completed | 2025-12-01 | 2025-12-01 | Breakeven Bar chart
rename scenario | Completed | 2025-12-02 | 2025-12-02 | projectcontext.js scenariotabs.js
prefix M on y-axis title | Completed | 2025-12-02 | 2025-12-02 | Breakevenbarchart.js
remove mass fraction | Completed | 2025-12-03 | 2025-12-03 | Biofuelform.js analysisdashboard.js
change hydrogen and electricity unit outputs | Completed | 2025-12-04 | 2025-12-05 | analysisdashboard.js | change only in frontend
delete history | Completed | 2025-12-10 | 2025-12-10 | backend\app\main.py frontend\src\api\projectApi.js frontend\src\contexts\ProjectContext.js frontend\src\components\project\ProjectStartupModal.js | change in backend and frontend
add fontweight to text below breakeven analysis | Completed | 2025-12-10 | 2025-12-10 | frontend\src\views\AnalysisDashboard.js | fontweight 400
add fontweight to scenario inputs subtitles | Completed | 2025-12-12 | 2025-12-12 | frontend\src\forms\BiofuelForm.js | fontweight 400
scenario.json got corrupted | Completed | 2025-12-12 | 2025-12-12 | backend\app\mock_database.py | will use postgresql in production
lcop pie/stacked bar charts | Completed | 2025-12-12 | 2025-12-12 | frontend\src\components\charts\LcopCostChart.js frontend\src\views\AnalysisDashboard.js | double animation glitch (backend problem)